## Sheet1
Job Status | Unit | Job ID | Area | System No | Equipment TAG No | Job Description / Notification Description | PM/Non-PM | Work Order No | Discipline | Workshop | Additional details | Scheduled Dropped on | Actual dropped on | Actual received in Laydown area | Actual Send to Workshop | Actual receive in Workshop | Actual out from workshop | Actual Received in Laydown area after O/H | Picked up for Installation | Scheduled for installation | Installed on | Final Handover to Operation | Size & Rating | Valve Type | Make | Link for Valve reports & Photos | Unit Inspection required | Finding / Discoveries | Remarks/Comments
Pending | EG-1 | EG1-004 | Oxide | 64 | MXK-LV-6404-03AR | 12Y O/H OF MXK-LV-6404-03AR AT VLV SHOP | PM | 20473566 | CV-OH | Almeer |  | 26/01/2025 | [7 empty] | 28/01/2025 |  |  | 1 -1/2 "X300# | Globe
Pending | EG-1 | EG1-006 | Glycol | 68 | MXK-HV-6822-03R | 6Y LOPA O/H, PROF TST OF MXK-HV-6822-03R | PM | 10275329 | CV-OH | Almeer |  | 22/01/2025 | [7 empty] | 28/01/2025 |  |  | 12"X300# | Butterfly |  |  | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-013 | Glycol | 68 | MXK-HV-6852-02R | 6Y LOPA O/H, PROOF TEST MXK-HV-6852-02R | PM | 10275330 | CV-OH | Almeer |  | 18/01/2025 | [7 empty] | 29/01/2025 |  |  | 4"X300# | Ball |  |  | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-017 | Oxide | 61 | MXK-PV-6130-08R | 7.5Y VALVE O/H MXK-PV-6130-08R MTL REQD | PM | 20586532 | CV-OH | KOMC |  | 20/01/2025 | [7 empty] | 26/01/2025 |  |  | 6"X600# | Butterfly |  |  | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-030 | Glycol | 68 | MXK-FV-6811-09 | 12Y O/H MXK-FV-6811-09 VLV,ACTR AT W/S | PM | 20621573 | CV-OH | KOMC |  | 21/01/2025 | [7 empty] | 28/01/2025 |  |  | 1-1/2"X 300# | Globe
Pending | EG-1 | EG1-031 | Glycol | 68 | MXK-FV-6851-05 | 12Y O/H MXK-FV-6851-05 VLV,ACTR AT W/S | PM | 20621575 | CV-OH | KOMC |  | 18/01/2025 | [7 empty] | 29/01/2025 |  |  | 1"X150# | Globe
Pending | EG-1 | EG1-032 | Glycol | 62 | MXK-FV-6213-01 | 12Y O/H OF MXK-FV-6213-01 AT VLV SHOP | PM | 20629201 | CV-OH | KOMC |  | 22/01/2025 | [7 empty] | 27/01/2025 |  |  | 6"X300# | Rotary Globe
Pending | EG-1 | EG1-033 | Glycol | 62 | MXK-FV-6223-01 | 6Y OH VLV,ACTUTR, PRF TST MXK-FV-6223-01 | PM | 20424000 | CV-OH | KOMC |  | 17/01/2025 | [7 empty] | 25/01/2025 |  |  | 3"X300# | Globe
Pending | EG-1 | EG1-034 | Oxide | 83 | MXK-HV-8300-39 | 12Y O/H OF MXK-HV-8300-39 AT VLV SHOP | PM | 20635974 | CV-OH | Al-Juliah |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 1"X150# | Ball
Pending | EG-1 | EG1-036 | Oxide | 61 | MXK-FV-6104-01R | 8Y O/H, REPL ACCESRS OF MXK-FV-6104-01R | PM | 20621569 | CV-OH | Almeer |  | 20/01/2025 | [7 empty] | 26/01/2025 |  |  | 6"X600# | Globe
Pending | EG-1 | EG1-037 | Glycol | 68 | MXK-FV-6822-01R | 6Y O/H,ACCESRS REPL,PROOF TST FV-6822-01 | PM | 20621574 | CV-OH | KOMC |  | 21/01/2025 | [7 empty] | 28/01/2025 |  |  | 10"X300# | Globe
Pending | EG-1 | EG1-040 | Glycol | 62 | MXK-HV-6221-21 | 8Y O/H, REPL ACCESRS OF MXK-HV-6221-21 | PM | 20627818 | CV-OH | Al-Juliah |  | 17/01/2025 | [7 empty] | 25/01/2025 |  |  | 1-1/2"X150 | Ball
Pending | EG-1 | EG1-041 | Oxide | 63 | MXK-LV-6301-07 | 8Y VLV OH, REPL ACCESRS MXK-LV-6301-07 | PM | 20629200 | CV-OH | KOMC |  | 23/01/2025 | [7 empty] | 28/01/2025 |  |  | 3"X300# | Rotary Globe
Pending | EG-1 | EG1-046 | Oxide | 74 | MXK-HV-7400-10 | 8Y VLV OH, REPL ACCESRS MXK-HV-7400-10 | PM | 20629199 | CV-OH | KOMC |  | 23/01/2025 | [7 empty] | 27/01/2025 |  |  | 1"X150# | 3 Way
Pending | EG-1 | EG1-048 | Oxide | 61 | MXK-HV-6116-90 | 8Y VLV OH, REPL ACCESRS MXK-HV-6116-90 | PM | 20629938 | CV-OH | Al-Juliah |  | 23/01/2025 | [7 empty] | 26/01/2025 |  |  | 6"X300# | Ball
Pending | EG-1 | EG1-049 | Glycol | 67 | MXK-FV-6733-01 | 8Y O/H, REPL ACCESRS OF MXK-FV-6733-01 | PM | 20621572 | CV-OH | KOMC |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 16"X300# | Butterfly
Pending | EG-1 | EG1-050 | Glycol | 68 | MXK-HV-6851-18 | 8Y VLV OH, REPL ACCESRS MXK-HV-6851-18 | PM | 20625210 | CV-OH | Al-Juliah |  | 18/01/2025 | [7 empty] | 29/01/2025 |  |  | 1-1/2"X150 | Ball
Pending | EG-1 | EG1-051 | Oxide | 63 | MXK-FV-6307-01 | 8Y O/H, REPL ACCESRS OF MXK-FV-6307-01 | PM | 20621571 | CV-OH | KOMC |  | 22/01/2025 | [7 empty] | 28/01/2025 |  |  | 14"X150# | Butterfly
Pending | EG-1 | EG1-052 | Glycol | 62 | MXK-LV-6213-03 | 12Y O/H OF MXK-LV-6213-03 AT VLV SHOP | PM | 20629202 | CV-OH | KOMC |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 2"X150# | Globe
Pending | EG-1 | EG1-055 | Oxide | 72 | MXK-HV-7202-28 | 6Y OH, LOPA PROF TST MXK-HV-7202-28 MTRL | PM | 20631995 | CV-OH | Al-Juliah |  | 21/01/2025 | [7 empty] | 25/01/2025 |  |  | 2"X150# | Ball |  |  | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-057 | Oxide | 66 | MXK-HV-6601-08C | 6Y PM O/H,LOPA PROF TEST MXK-HV-6601-08C | PM | 20631673 | CV-OH | Al-Juliah |  | 23/01/2025 | [7 empty] | 27/01/2025 |  |  | 3/4"X600# | Ball |  |  | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-058 | Glycol | 62 | MXK-HV-6223-02R | 6Y PM O/H,LOPA PROF TEST MXK-HV-6223-02R | PM | 20517559 | CV-OH | Al-Juliah |  | 17/01/2025 | [7 empty] | 25/01/2025 |  |  | 3"X300# | Butterfly |  |  | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-059/343 | Oxide | 66 | MXK-HV-6601-08B | 6Y PM O/H,LOPA PROF TEST MXK-HV-6601-08B | PM/RM | 20631672 | CV-OH | Almeer |  | 23/01/2025 | [7 empty] | 27/01/2025 |  |  | 6"X600# | Ball |  |  | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-108 | Oxide | 64 | MXK-HV-6404-25 | 2.5Y LOPA PRF TST AT SITE MXK-HV-6404-25 | PM | 20621696 | CV-OH | Almeer |  | 21/01/2025 | [7 empty] | 25/01/2025 |  |  | 6"X150# | Ball |  |  | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-294 | Glycol | 62 | MXK-FV-6202-02R | 12Y O/H OF MXK-FV-6202-02R AT VLV SHOP | PM | 20642903 | CV-OH | KOMC |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 6"X300# | Globe
Pending | EG-1 | EG1-296 | Oxide | 63 | MXK-FV-6301-17 | 12Y O/H OF MXK-FV-6301-17 AT VLV SHOP | PM | 20642908 | CV-OH | KOMC |  | 25/01/2025 | [7 empty] | 28/01/2025 |  |  | 8"X300# | Globe
Pending | EG-1 | EG1-299 | Glycol | 67 | MXK-HV-6718-02 | 12Y O/H OF MXK-HV-6718-02 AT VLV SHOP | PM | 20642902 | CV-OH | Almeer |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 1"X300# | Ball
Pending | EG-1 | EG1-301 | Oxide | 81 | MXK-HV-8107-02A | 7.5Y VALVE O/H MXK-HV-8107-02A MTL REQD | PM | 20621576 | CV-OH | Almeer |  | 20/01/2025 | [7 empty] | 26/01/2025 |  |  | 6"X600# | Ball
Pending | EG-1 | EG1-302 | Oxide | 81 | MXK-HV-8107-02B | 7.5Y VALVE O/H MXK-HV-8107-02B MTL REQD | PM | 20621577 | CV-OH | Almeer |  | 20/01/2025 | [7 empty] | 26/01/2025 |  |  | 6"X600# | Ball
Pending | EG-1 | EG1-305 | Oxide | 63 | MXK-LV-6306-02A | 12Y O/H OF MXK-LV-6306-02A AT VLV SHOP | PM | 20642914 | CV-OH | Almeer |  | 24/01/2025 | [7 empty] | 28/01/2025 |  |  | 4"X150# | Ball
Pending | EG-1 | EG1-306 | Oxide | 63 | MXK-LV-6306-02B | 12Y O/H OF MXK-LV-6306-02B AT VLV SHOP | PM | 20642915 | CV-OH | Almeer |  | 24/01/2025 | [7 empty] | 28/01/2025 |  |  | 4"X300# | Ball
Pending | EG-1 | EG1-307 | Oxide | 63 | MXK-LV-6306-02C | 12Y O/H OF MXK-LV-6306-02C AT VLV SHOP | PM | 20642916 | CV-OH | Almeer |  | 24/01/2025 | [7 empty] | 28/01/2025 |  |  | 4"X150# | Ball
Pending | EG-1 | EG1-308 | Glycol | 68 | MXK-LV-6814-01 | 12Y O/H OF MXK-LV-6814-01 AT VLV SHOP | PM | 20642918 | CV-OH | KOMC |  | 21/01/2025 | [7 empty] | 27/01/2025 |  |  | 3"X300# | Globe
Pending | EG-1 | EG1-382 | Oxide | 64 | MXK-HV-6422-05AR | overhauling to be done | PM | 10275435 | CV-OH | Al-Juliah |  | 25/01/2025 | [7 empty] | 28/01/2025 |  |  | 20"X150# | Butterfly
Pending | EG-1 | EG1-383 | Oxide | 64 | MXK-HV-6422-05BR | overhauling to be done | PM | 10275436 | CV-OH | Al-Juliah |  | 25/01/2025 | [7 empty] | 28/01/2025 |  |  | 24"X150# | Butterfly
Pending | EG-1 | EG1-384 | Oxide | 64 | MXK-HV-6422-05CR | overhauling to be done | PM | 10275449 | CV-OH | Al-Juliah |  | 24/01/2025 | [7 empty] | 26/01/2025 |  |  | 20"X150# | Butterfly
Pending | EG-1 | EG1-385 | Oxide | 64 | MXK-HV-6422-05DR | overhauling to be done | PM | 10275450 | CV-OH | Al-Juliah |  | 24/01/2025 | [7 empty] | 26/01/2025 |  |  | 24"X150# | Butterfly
Pending | EG-1 | EG1-386 | Oxide | 64 | MXK-HV-6446-05AR | overhauling to be done | PM | 10275451 | CV-OH | Al-Juliah |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 16"X150# | Butterfly
Pending | EG-1 | EG1-387 | Oxide | 64 | MXK-HV-6446-05BR | overhauling to be done | PM | 10275452 | CV-OH | Al-Juliah |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 16"X150# | Butterfly
Pending | EG-1 | EG1-388 | Oxide | 64 | MXK-HV-6446-05CR | overhauling to be done | PM | 10275453 | CV-OH | Al-Juliah |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 16"X150# | Butterfly
Pending | EG-1 | EG1-389 | Oxide | 64 | MXK-HV-6446-05DR | overhauling to be done | PM | 10275454 | CV-OH | Al-Juliah |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 16"X150# | Butterfly
Pending | EG-1 | EG1-406 | Oxide | 64 | MXK-HV-6401-06R | MXK-HV-6401-06R actuator to be replaced due to vibration issue | PM | 10275455 | CV-OH | KOMC |  | 21/01/2025 | [7 empty] | 25/01/2025 |  |  | 10"X300# | Butterfly |  |  | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-407 | Oxide | 61 | MXK-PV-6116-06 | MXK-PV-6116-06 valve body sub assembly to be replaced like to like as per recommendation from Process automation design engineer (Muthu). | PM | 10275456 | CV-OH | KOMC |  | 20/01/2025 | [7 empty] | 26/01/2025 |  |  | 4"X300# | Globe
Pending | EG-1 | EG1-408 | Oxide | 61 | MXK-FV-6130-02 | MXK-FV-6130-02 valve body sub assembly to be replaced like to like | PM | 10275457 | CV-OH | KOMC |  | 20/01/2025 | [7 empty] | 26/01/2025 |  |  | 1.5"X600# | Angle
Pending | EG-1 | EG1-432 | Glycol | 62 | MXK-HV-6260-03 | passing and not functioning properly needs to be attended MAIN WO-10254408-SUB WO-10254409 | PM | 10254408 | CV-OH | Almeer |  | 22/01/2025 | [7 empty] | 27/01/2025 |  |  | 3/4"X300# | Ball
Pending | EG-1 | EG1-AJ-19 | Oxide | 72 | MXK-HV-7202-26 | 6Y PM O/H, LOPA PROOF TEST MXK-HV-7202-26 | PM | 20631674 | CV-OH | Al-Juliah |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 2"X150# | Ball |  |  | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-AJ-36 | Glycol | 62 | MXK-PV-6211-11 | Drop and Inspect | PM | 10286513 | CV-OH | MFT-3 |  | 26/01/2025 | [7 empty] | 27/01/2025 |  |  | 2"X300# | Globe
Pending | EG-1 | EG1-065 | Glycol | 62 | MXK-PSV-6213-800 | 2Y PM MXK-PSV-6213-800 SAME DAY RETURN | PM | 20610910 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 26/01/2025 |  |  | 4 X 6 IN
Pending | EG-1 | EG1-066 | Oxide | 64 | MXK-PSV-6404-802R | 2Y PM OF MXK-PSV-6404-802R | PM | 20610951 | PSV-OH | MFT-3 | EO Service | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 1 X3/4 IN
Pending | EG-1 | EG1-068 | Glycol | 68 | MXK-PSV-6821-801 | 2Y PM OF MXK-PSV-6821-801 SAMEDAY RETN | PM | 20611059 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 6 X 8 IN
Pending | EG-1 | EG1-069 | Glycol | 67 | MXK-PSV-6701-800 | 2Y PM MXK-PSV-6701-800-(80T CRANE REQD) | PM | 20611030 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 26/01/2025 |  |  | 6 X 8 IN
Pending | EG-1 | EG1-074 | Oxide | 66 | MXK-PSV-6608-800 | 4Y GMISS PM MXK-PSV-6608-800 SAMEDAY RET | PM | 20611006 | PSV-OH | MFT-3 | Sensor | 21/01/2025 | [7 empty] | 26/01/2025 |  |  | 2 X 3 IN
Pending | EG-1 | EG1-079 | Glycol | 62 | MXK-PSV-6243-804 | 3Y GMISS PM MXK-PSV-6243-804 SAMEDAY RET | PM | 20610931 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-080 | Glycol | 68 | MXK-PSV-6853-800 | 3Y GMIS PM PSV-6853-800 SAMEDY RET,CRANE | PM | 20611073 | PSV-OH | MFT-3 |  | 18/01/2025 | [7 empty] | 28/01/2025 |  |  | 3 X 4 IN
Pending | EG-1 | EG1-105 | Oxide | 63 | MXK-PSV-6310-800 | 2.5Y PSV PM OF MXK-PSV-6310-800 CAT S/D | PM | 20631465 | PSV-OH | MFT-3 |  | 25/01/2025 | [7 empty] | 27/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-106 | Oxide | 63 | MXK-PSV-6311-800 | 2.5Y PSV PM OF MXK-PSV-6311-800 CAT S/D | PM | 20631466 | PSV-OH | MFT-3 |  | 26/01/2025 | [7 empty] | 28/01/2025 |  |  | 1X2 IN
Pending | EG-1 | EG1-118 | Glycol | 68 | MXK-PSV-6854-800 | 4.5Y PM OF MXK-PSV-6854-800 | PM | 20611074 | PSV-OH | MFT-3 |  | 19/01/2025 | [7 empty] | 28/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-119 | Glycol | 68 | MXK-PSV-6857-800 | 4.5Y PM OF MXK-PSV-6857-800 | PM | 20611075 | PSV-OH | MFT-3 |  | 19/01/2025 | [7 empty] | 28/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-120 | Glycol | 62 | MXK-PSV-6222-800 | 4.5Y PM OF MXK-PSV-6222-800 | PM | 20610913 | PSV-OH | MFT-3 |  | 17/01/2025 | [7 empty] | 27/01/2025 |  |  | 2 X 3 IN
Pending | EG-1 | EG1-121 | Oxide | 61 | MXK-PSV-6111-800 | 4.5Y PM OF MXK-PSV-6111-800 | PM | 20610888 | PSV-OH | MFT-3 |  | 20/01/2025 | [7 empty] | 27/01/2025 |  |  | 6 X 10 IN
Pending | EG-1 | EG1-122 | Oxide | 64 | MXK-PSV-6496-800 | 4.5Y PM OF MXK-PSV-6496-800 | PM | 20610991 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 27/01/2025 |  |  | 1-1/2 X 2 IN
Pending | EG-1 | EG1-123 | Glycol | 67 | MXK-PSV-6702-800 | 4.5Y GMISS PM OF MXK-PSV-6702-800 | PM | 20611031 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 26/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-124 | Glycol | 87 | MXK-PSV-8701-800 | 4.5Y PM MXK-PSV-8701-800 SAMEDAY RETURN | PM | 20611134 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 27/01/2025 |  |  | 1/2 X 1 IN
Pending | EG-1 | EG1-125 | Oxide | 61 | MXK-PSV-6130-801 | 4.5Y PM OF MXK-PSV-6130-801 35T CR | PM | 20610898 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 27/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-126 | Glycol | 62 | MXK-PSV-6212-800 | 4.5Y PM OF MXK-PSV-6212-800 SAME DAY | PM | 20610909 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 26/01/2025 |  |  | 1-1/2 X 2-1/2 IN
Pending | EG-1 | EG1-127 | Oxide | 63 | MXK-PSV-6302-800 | 4.5Y PM OF MXK-PSV-6302-800 | PM | 20610938 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 28/01/2025 |  |  | 2 X 3 IN
Pending | EG-1 | EG1-128 | Glycol | 67 | MXK-PSV-6703-800 | 4.5Y GMISS PM OF MXK-PSV-6703-800 | PM | 20611032 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 26/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-129 | Glycol | 68 | MXK-PSV-6825-800 | 4.5Y PM OF MXK-PSV-6825-800 | PM | 20611063 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 24/01/2025 |  |  | 1-1/2 X 2 IN
Pending | EG-1 | EG1-130 | Glycol | 68 | MXK-PSV-6825-803 | 4.5Y GMISS PM PSV-6825-803 SAMEDAY RETN | PM | 20611066 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 27/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-131 | Glycol | 68 | MXK-PSV-6846-801 | 4.5Y PM OF MXK-PSV-6846-801 | PM | 20611070 | PSV-OH | MFT-3 |  | 18/01/2025 | [7 empty] | 28/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-132 | Glycol | 87 | MXK-PSV-8701-801 | 4.5Y PM MXK-PSV-8701-801 SAMEDAY RETURN | PM | 20611135 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 27/01/2025 |  |  | 1/2 X 1 IN
Pending | EG-1 | EG1-133 | Oxide | 74 | MXK-PSV-7400-805 | 4.5Y PM OF MXK-PSV-7400-805 | PM | 20612341 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 26/01/2025 |  |  | 1/4 X 1/4 IN
Pending | EG-1 | EG1-134 | Glycol | 62 | MXK-PSV-6202-800 | 4.5Y PM OF MXK-PSV-6202-800-INSTR SUPPOR | PM | 20610903 | PSV-OH | MFT-3 | EO Service ,Sensor | 22/01/2025 | [7 empty] | 24/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-135 | Glycol | 67 | MXK-PSV-6708-800 | 4.5Y PM OF MXK-PSV-6708-800 | PM | 20611034 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 26/01/2025 |  |  | 6 X 8 IN
Pending | EG-1 | EG1-136 | Glycol | 68 | MXK-PSV-6811-800 | 4.5Y PM OF MXK-PSV-6811-800 | PM | 20611055 | PSV-OH | MFT-3 |  | 20/01/2025 | [7 empty] | 28/01/2025 |  |  | 4 X 6 IN
Pending | EG-1 | EG1-137 | Glycol | 68 | MXK-PSV-6814-800 | 4.5Y PM OF MXK-PSV-6814-800 CAT S/D | PM | 20611056 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 2-1/2 X 4 IN
Pending | EG-1 | EG1-138 | Glycol | 68 | MXK-PSV-6825-802 | 4.5Y PM OF MXK-PSV-6825-802 | PM | 20611065 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-139 | Glycol | 68 | MXK-PSV-6846-802 | 4.5Y PM OF MXK-PSV-6846-802(80TON CRANE) | PM | 20611071 | PSV-OH | MFT-3 |  | 18/01/2025 | [7 empty] | 28/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-140 | Glycol | 68 | MXK-PSV-6861-800 | 4.5Y PM OF MXK-PSV-6861-800 | PM | 20611077 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 28/01/2025 |  |  | 2-1/2 X 4 IN
Pending | EG-1 | EG1-141 | Glycol | 68 | MXK-PSV-6823-800 | 4.5Y PM OF MXK-PSV-6823-800 | PM | 20611061 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 6 X 8 IN
Pending | EG-1 | EG1-142 | Oxide | 72 | MXK-PSV-7201-800 | 4.5Y PM OF MXK-PSV-7201-800 | PM | 20611091 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 27/01/2025 |  |  | 1-1/2 X 2-1/2 IN
Pending | EG-1 | EG1-143 | Oxide | 72 | MXK-PSV-7207-800 | 4.5Y PM OF MXK-PSV-7207-800 | PM | 20611095 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 27/01/2025 |  |  | 2 X 3 IN
Pending | EG-1 | EG1-144 | Glycol | 81 | MXK-PSV-8101-801 | 4.5Y PM OF MXK-PSV-8101-801 CAT S/D | PM | 20611113 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 2 X 3 IN
Pending | EG-1 | EG1-154 | Glycol | 62 | MXK-PSV-6223-800 | 3Y GMISS PM MXK-PSV-6223-800 SAMEDAY RET | PM | 20610914 | PSV-OH | MFT-3 |  | 17/01/2025 | [7 empty] | 27/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-155 | Glycol | 62 | MXK-PSV-6221-800 | 3Y PM OF MXK-PSV-6221-800 | PM | 20610912 | PSV-OH | MFT-3 |  | 17/01/2025 | [7 empty] | 26/01/2025 |  |  | 6 X 8 IN
Pending | EG-1 | EG1-156 | Glycol | 62 | MXK-PSV-6223-801 | 3Y PM OF MXK-PSV-6223-801 | PM | 20610915 | PSV-OH | MFT-3 |  | 18/01/2025 | [7 empty] | 27/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-157 | Glycol | 62 | MXK-PSV-6224-800 | 3Y GMISS PM MXK-PSV-6224-800 SCAF,SAMEDY | PM | 20610916 | PSV-OH | MFT-3 |  | 18/01/2025 | [7 empty] | 27/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-158 | Oxide | 64 | MXK-PSV-6478-800 | 3Y GMISS PM OF MXK-PSV-6478-800 | PM | 20610987 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 26/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-159 | Glycol | 68 | MXK-PSV-6851-800 | 3Y GMISS PM OF MXK-PSV-6851-800 | PM | 20611072 | PSV-OH | MFT-3 |  | 18/01/2025 | [7 empty] | 28/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-160 | Glycol | 62 | MXK-PSV-6240-802 | 3Y PM OF MXK-PSV-6240-802 SAMEDAY RETURN | PM | 20610924 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-164 | Oxide | 61 | MXK-PSV-6116-807 | 3Y PM MXK-PSV-6116-807 (S/D) CAT CHANGE | PM | 20610896 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 26/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-165 | Oxide | 61 | MXK-PSV-6116-808 | 3Y PM MXK-PSV-6116-808 (S/D) CAT CHANGE | PM | 20610897 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 26/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-166 | Glycol | 62 | MXK-PSV-6202-801 | 3Y GMISS PM MXK-PSV-6202-801 SAMEDAY RET | PM | 20610904 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 26/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-167 | Glycol | 62 | MXK-PSV-6211-800 | 3Y GMISS PM MXK-PSV-6211-800 SAMEDAY RET | PM | 20610907 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 26/01/2025 |  |  | 6 X 10 IN
Pending | EG-1 | EG1-168 | Glycol | 62 | MXK-PSV-6213-801 | 3Y GMISS PM MXK-PSV-6213-801 SAMEDAY RET | PM | 20610911 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 26/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-210 | Oxide | 61 | MXK-PSV-6116-801 | 3Y PM OF MXK-PSV-6116-801 | PM | 20610890 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 2 X 3 IN
Pending | EG-1 | EG1-211 | Oxide | 61 | MXK-PSV-6116-802 | 3Y GMISS PM MXK-PSV-6116-802 SAMEDAY RET | PM | 20610891 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 2 X 3 IN
Pending | EG-1 | EG1-212 | Oxide | 61 | MXK-PSV-6116-805 | 3Y PM OF MXK-PSV-6116-805 | PM | 20610894 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-213 | Glycol | 62 | MXK-PSV-6241-800 | 3Y GMISS PM MXK-PSV-6241-800 SAMEDAY RET | PM | 20610925 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-214 | Glycol | 67 | MXK-PSV-6780-800R | 3Y GMISS PM OF MXK-PSV-6780-800R | PM | 20642899 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 26/01/2025 |  |  | 4" 300/6" 150
Pending | EG-1 | EG1-215 | Oxide | 64 | MXK-PSV-6422-800 | 3Y GMISS PM OF MXK-PSV-6422-800 | PM | 20610961 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 28/01/2025 |  |  | 2 X 3 IN
Pending | EG-1 | EG1-216 | Oxide | 74 | MXK-PSV-7400-800 | 3Y GMISS PM OF MXK-PSV-7400-800 | PM | 20611096 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 26/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-217 | Glycol | 81 | MXK-PSV-8100-800 | 3Y GMISS PM OF MXK-PSV-8100-800 | PM | 20611105 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 25/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-218 | Oxide | 63 | MXK-PSV-6351-800 | 3Y GMISS PM MXK-PSV-6351-800 CAT CHANGE | PM | 20610945 | PSV-OH | MFT-3 |  | 25/01/2025 | [7 empty] | 27/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-219 | Oxide | 64 | MXK-PSV-6417-800 | 3Y GMISS PM OF MXK-PSV-6417-800 | PM | 20610955 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-220 | Oxide | 64 | MXK-PSV-6417-801 | 3Y GMISS PM OF MXK-PSV-6417-801 | PM | 20610956 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 26/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-221 | Oxide | 64 | MXK-PSV-6418-800 | 3Y GMISS PM OF MXK-PSV-6418-800-35T CR | PM | 20610957 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 26/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-222 | Oxide | 64 | MXK-PSV-6418-801 | 3Y PM OF MXK-PSV-6418-801-35T CR | PM | 20610958 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 27/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-223 | Oxide | 83 | MXK-PSV-8300-802 | 3Y PM OF MXK-PSV-8300-802 | PM | 20611133 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 27/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-224 | Oxide | 74 | MXK-PSV-7400-806 | 3Y GMISS PM OF MXK-PSV-7400-806 | PM | 20612342 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 26/01/2025 |  |  | 1/4 X 1/4 IN
Pending | EG-1 | EG1-225 | Oxide | 61 | MXK-PSV-6116-086 | 3Y PM OF MXK-PSV-6116-086 | PM | 20610889 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 24/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-226 | Oxide | 64 | MXK-PSV-6405-800 | 3Y GMISS PM OF MXK-PSV-6405-800 | PM | 20610952 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 1-1/2 X 2-1/2 IN
Pending | EG-1 | EG1-227 | Oxide | 64 | MXK-PSV-6446-800 | 3Y GMISS PM OF MXK-PSV-6446-800 | PM | 20610964 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 28/01/2025 |  |  | 1-1/2 X 3 IN
Pending | EG-1 | EG1-228 | Oxide | 61 | MXK-PSV-6116-803 | 3Y PM MXK-PSV-6116-803 (S/D) CAT CHANGE | PM | 20610892 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-229 | Oxide | 61 | MXK-PSV-6116-804 | 3Y PM MXK-PSV-6116-804 (S/D) CAT CHANGE | PM | 20610893 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-230 | Glycol | 67 | MXK-PSV-6774-801 | 3Y GMISS PM OF MXK-PSV-6774-801 | PM | 20611049 | PSV-OH | MFT-3 |  | 25/01/2025 | [7 empty] | 27/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-231 | Glycol | 67 | MXK-PSV-6776-802 | 3Y GMISS PM MXK-PSV-6776-802 INSTR SUPRT | PM | 20611050 | PSV-OH | MFT-3 | EO Service ,Sensor | 25/01/2025 | [7 empty] | 26/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-232 | Glycol | 68 | MXK-PSV-6821-800 | 3Y GMIS PM MXK-PSV-6821-800 SAMEDAY RETN | PM | 20611058 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-233 | Glycol | 81 | MXK-PSV-8103-800 | 3Y GMISS PM OF MXK-PSV-8103-800 | PM | 20611115 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 26/01/2025 |  |  | 1-1/2 X 3 IN
Pending | EG-1 | EG1-234 | Oxide | 64 | MXK-PSV-6404-801 | 3Y PM OF MXK-PSV-6404-801-INSTR SUPPORT | PM | 20610950 | PSV-OH | MFT-3 | EO Service | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 6 X 10 IN
Pending | EG-1 | EG1-235 | Glycol | 67 | MXK-PSV-6712-800 | 3Y GMISS PM OF MXK-PSV-6712-800 | PM | 20611038 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 27/01/2025 |  |  | 6 X 10 IN
Pending | EG-1 | EG1-236 | Glycol | 81 | MXK-PSV-8110-801 | 3Y GMISS PM OF MXK-PSV-8110-801 | PM | 20611120 | PSV-OH | MFT-3 |  | 25/01/2025 | [7 empty] | 27/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-238 | Oxide | 61 | MXK-PSV-6130-803 | 3Y GMISS PM OF MXK-PSV-6130-803-35T CR | PM | 20610900 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 26/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-239 | Glycol | 62 | MXK-PSV-6240-800 | 3Y GMISS PM MXK-PSV-6240-800 SAMEDAY RET | PM | 20610922 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 28/01/2025 |  |  | 24 IN
Pending | EG-1 | EG1-240 | Glycol | 62 | MXK-PSV-6240-801 | 3Y GMISS PM MXK-PSV-6240-801 CRAN,SAMEDY | PM | 20610923 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 28/01/2025 |  |  | 8 IN
Pending | EG-1 | EG1-241 | Oxide | 63 | MXK-PSV-6320-800 | 3Y GMISS PM OF MXK-PSV-6320-800 | PM | 20610943 | PSV-OH | MFT-3 |  | 25/01/2025 | [7 empty] | 27/01/2025 |  |  | 2 X 3 IN
Pending | EG-1 | EG1-242 | Oxide | 64 | MXK-PSV-6412-800 | 3Y GMISS PM OF MXK-PSV-6412-800 | PM | 20610953 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 3 X 4 IN
Pending | EG-1 | EG1-243 | Oxide | 64 | MXK-PSV-6456-800 | 3Y GMISS PM OF MXK-PSV-6456-800 | PM | 20610966 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 29/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-244 | Oxide | 64 | MXK-PSV-6458-800 | 3Y GMISS PM OF MXK-PSV-6458-800 | PM | 20610967 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 26/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-245 | Oxide | 64 | MXK-PSV-6485-800 | 3Y GMISS PM OF MXK-PSV-6485-800 | PM | 20610988 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 26/01/2025 |  |  | 3/4 X 1 IN
Pending | EG-1 | EG1-246 | Glycol | 67 | MXK-PSV-6709-800 | 3Y GMIS PM MXK-PSV-6709-800 SAMEDAY RETN | PM | 20611035 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 26/01/2025 |  |  | 2-1/2 X 4 IN
Pending | EG-1 | EG1-247 | Glycol | 67 | MXK-PSV-6710-800 | 3Y GMIS PM PSV-6710-800 SAMEDY RET,CRANE | PM | 20611036 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 27/01/2025 |  |  | 4 X 6 IN
Pending | EG-1 | EG1-248 | Glycol | 81 | MXK-PSV-8100-810 | 3Y PM OF MXK-PSV-8100-810-SHUTDOWN JOB | PM | 20611106 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 25/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-249 | Glycol | 81 | MXK-PSV-8100-811 | 3Y PM OF MXK-PSV-8100-811-SHUTDOWN JOB | PM | 20611107 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-250 | Glycol | 81 | MXK-PSV-8100-812 | 3Y PM OF MXK-PSV-8100-812-SHUTDOWN JOB | PM | 20611108 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-251 | Glycol | 81 | MXK-PSV-8100-813 | 3Y PM OF MXK-PSV-8100-813-SHUTDOWN JOB | PM | 20611109 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-252 | Glycol | 81 | MXK-PSV-8100-815 | 3Y PM OF MXK-PSV-8100-815-SHUTDOWN JOB | PM | 20611112 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-253 | Glycol | 81 | MXK-PSV-8101-802 | 3Y GMIS PM MXK-PSV-8101-802 SAMEDAY RETN | PM | 20611114 | PSV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 25/01/2025 |  |  | 2 X 3 IN
Pending | EG-1 | EG1-254 | Glycol | 81 | MXK-PSV-8103-803 | 3Y GMIS PM MXK-PSV-8103-803 SAMEDAY RETN | PM | 20611118 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 26/01/2025 |  |  | 4 X 6 IN
Pending | EG-1 | EG1-255 | Glycol | 81 | MXK-PSV-8107-801 | 3Y GMISS PM OF MXK-PSV-8107-801 | PM | 20611119 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 27/01/2025 |  |  | 6 X 8 IN
Pending | EG-1 | EG1-258 | Oxide | 61 | MXK-PSV-6130-802 | 3Y PM OF MXK-PSV-6130-802-35T CR | PM | 20610899 | PSV-OH | MFT-3 |  | 20/01/2025 | [7 empty] | 26/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-259 | Glycol | 81 | MXK-PSV-8100-814 | 3Y PM OF MXK-PSV-8100-814-SHUTDOWN JOB | PM | 20611110 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-260 | Oxide | 63 | MXK-PSV-6305-800 | 3Y GMISS PM OF MXK-PSV-6305-800 | PM | 20610940 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 28/01/2025 |  |  | 1 X 2 IN
Pending | EG-1 | EG1-261 | Oxide | 64 | MXK-PSV-6401-800 | 3Y GMISS PM MXK-PSV-6401-800 INSTR SUPRT | PM | 20610948 | PSV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 6 X 8 IN
Pending | EG-1 | EG1-262 | Glycol | 67 | MXK-PSV-6713-800 | 3Y GMISS PM OF MXK-PSV-6713-800 | PM | 20611039 | PSV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 27/01/2025 |  |  | 6 X 8 IN
Pending | EG-1 | EG1-263 | Glycol | 81 | MXK-PSV-8128-801R | 3Y PM OF MXK-PSV-8128-801R 50T CRANE | PM | 20611122 | PSV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 27/01/2025 |  |  | 4X6 IN
Pending | EG-1 | EG1-264 | Oxide | 64 | MXK-PSV-6404-800 | 3Y GMISS PM MXK-PSV-6404-800 INSTR SUPRT | PM | 20610949 | PSV-OH | MFT-3 | EO Service | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 8 X 10 IN
Pending | EG-1 | EG1-438 | Glycol | 67 | MXK-PSV-6779-801R2 | Valve to be dropped and inspected/tested | PM | 10275646 | PSV-OH | MFT-3 | EO Service | 22/01/2025 | [7 empty] | 26/01/2025 |  |  | 1-1/2"
Pending | EG-1 | EG1-109 | Oxide | 63 | MXK-CHK-6328 | 2.5Y CHECK VLV INSPN OF MXK-CHK-6328 | PM | 20640203 | MV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 28/01/2025 |  |  | 10"
Pending | EG-1 | EG1-111 | Oxide | 63 | MXK-CHK-6310 | 2.5Y CHECK VLV INSPN OF MXK-CHK-6310 | PM | 20640201 | MV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 28/01/2025 |  |  | 8"
Pending | EG-1 | EG1-113 | Oxide | 63 | MXK-CHK-6327 | 2.5Y CHECK VLV INSPN OF MXK-CHK-6327 | PM | 20640184 | MV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 28/01/2025 |  |  | 10"
Pending | EG-1 | EG1-117 | Oxide | 63 | MXK-CHK-6311 | 2.5Y CHECK VLV INSPN OF MXK-CHK-6311 | PM | 20640202 | MV-OH | MFT-3 |  | 23/01/2025 | [7 empty] | 28/01/2025 |  |  | 8"
Pending | EG-1 | EG1-AJ-30 | Glycol | 67 | MXK-FV-6733-01 | Full service for FV-6733-01 12" Bypass block valve | PM | 10285977 | MV-OH | MFT-3 |  | 24/01/2025 | [7 empty] | 27/01/2025 |  |  | 12"
Pending | EG-1 | EG1-381 | Glycol | 67 | MXK-PSV-6780-800R | provide new PSV and rupture disc as per MOC EG-11Dec2022-88207 | PM | 50041786 | PSV-Replacement |  |  | 26/01/2025 | [7 empty] | 26/01/2025 |  |  | 4 X6 IN
Pending | EG-1 | EG1-097 | Oxide | 61 | MXK-HV-6135-14AR | 2.5Y SPARE VLV REPL MXK-HV-6135-14AR S/D | PM | 20615234 | CV-Replacement |  | O2 Service | 27/01/2025 | [7 empty] | 28/01/2025 | [6 empty] | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-114 | Oxide | 61 | MXK-HV-6135-14BR | 2.5Y SPARE VLV REPL MXK-HV-6135-14BR S/D | PM | 20631094 | CV-Replacement |  | O2 Service | 27/01/2025 | [7 empty] | 28/01/2025 | [6 empty] | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-330 | Oxide | 63 | MXK-LV-6301-01 | MXK-LV-6301-01 installed valve in field to be dropped and inspected | PM | 10275433 | CV-Replacement |  |  | 22/01/2025 | [7 empty] | 26/01/2025
Pending | EG-1 | EG1-390 | Oxide | 61 | MXK-HV-6135-21 | Replacement of MXK-HV-6135-21 (MOV) | PM | 10275506 | CV-Replacement |  | O2 Service | 27/01/2025 | [7 empty] | 28/01/2025
Pending | EG-1 | EG1-411 | Glycol | 81 | MXK-PV-8110-06R | Replacement of MXK-PV-8110-06R with improved design as per technical study recommendation and MOC EG-16Jan2024-110805 | PM | 10275553 | CV-Replacement |  |  | 26/01/2025 | [7 empty] | 27/01/2025
Pending | EG-1 | EG1-038 | Oxide | 64 | MXK-HV-6417-05R2 | 8Y ON SITE ACCESRS REPLMNT HV-6417-05R2 | PM | 20636083 | CV-Online | KOMC |  | 26/01/2025 | [7 empty] | 26/01/2025
Pending | EG-1 | EG1-039 | Oxide | 61 | MXK-LV-6107-01 | 8Y ACCESORIS REPL AT SITE MXK-LV-6107-01 | PM | 20635980 | CV-Online | KOMC |  | 23/01/2025 | [7 empty] | 23/01/2025
Pending | EG-1 | EG1-042 | Glycol | 68 | MXK-FV-6821-13 | 8Y ACCESORIS REPL AT SITE MXK-FV-6821-13 | PM | 20635977 | CV-Online | KOMC |  | 28/01/2025 | [7 empty] | 29/01/2025
Pending | EG-1 | EG1-043 | Glycol | 68 | MXK-FV-6851-15 | 8Y ACCESORIS REPL AT SITE MXK-FV-6851-15 | PM | 20635978 | CV-Online | KOMC |  | 27/01/2025 | [7 empty] | 28/01/2025
Pending | EG-1 | EG1-044 | Oxide | 63 | MXK-LV-6305-17 | 8Y ACCESORIS REPL AT SITE MXK-LV-6305-17 | PM | 20635982 | CV-Online | KOMC |  | 24/01/2025 | [7 empty] | 25/01/2025
Pending | EG-1 | EG1-045 | Oxide | 63 | MXK-LV-6351-01 | 8Y ACCESORIS REPL AT SITE MXK-LV-6351-01 | PM | 20635983 | CV-Online | KOMC |  | 24/01/2025 | [7 empty] | 24/01/2025
Pending | EG-1 | EG1-047 | Oxide | 63 | MXK-LV-6305-12 | 8Y ACCESORIS REPL AT SITE MXK-LV-6305-12 | PM | 20635981 | CV-Online | KOMC |  | 25/01/2025 | [7 empty] | 25/01/2025
Pending | EG-1 | EG1-071 | Oxide | 66 | MXK-HV-6631-09 | 2.5Y FUNCT: TEST-VALVES- CAT CH -3 TAGS | PM | 20628925 | CV-Online | KOMC |  | 26/01/2025 | [7 empty] | 27/01/2025
Pending | EG-1 | EG1-110 | Oxide | 61 | MXK-HV-6135-14CR | 2.5Y FUNCTN TST AT SITE MXK-HV-6135-14CR | PM | 20615390 | CV-Online | KOMC | O2 Service | 21/01/2025 | [7 empty] | 22/01/2025 | [6 empty] | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-112 | Oxide | 61 | MXK-HV-6135-14DR | 2.5Y FUNCTN TST AT SITE MXK-HV-6135-14DR | PM | 20615391 | CV-Online | KOMC | O2 Service | 22/01/2025 | [7 empty] | 22/01/2025 | [6 empty] | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-115 | Oxide | 61 | MXK-HV-6135-55B | 2.5Y FUNCTION TEST AT SITE-CAT CHANGE | PM | 20615392 | CV-Online | KOMC | O2 Service | 22/01/2025 | [7 empty] | 23/01/2025 | [6 empty] | Yes |  | NEED UNIT INSPECTION BEFORE AND AFTER O/H
Pending | EG-1 | EG1-148 | Oxide | 64 | MXK-LV-6496-01 | 8Y ACCESORIS REPL AT SITE MXK-LV-6496-01 | PM | 20635984 | CV-Online | KOMC |  | 25/01/2025 | [7 empty] | 26/01/2025
Pending | EG-1 | EG1-295 | Glycol | 62 | MXK-FV-6213-01 | 8Y ACCESORIS REPL AT SITE MXK-FV-6213-01 | PM | 20642925 | CV-Online | KOMC |  | 23/01/2025 | [7 empty] | 24/01/2025
Pending | EG-1 | EG1-297 | Glycol | 68 | MXK-FV-6811-09 | 8Y ACCESORIS REPL AT SITE MXK-FV-6811-09 | PM | 20642931 | CV-Online | KOMC |  | 28/01/2025 | [7 empty] | 28/01/2025
Pending | EG-1 | EG1-298 | Glycol | 68 | MXK-FV-6851-05 | 8Y ACCESORIS REPL AT SITE MXK-FV-6851-05 | PM | 20642932 | CV-Online | KOMC |  | 28/01/2025 | [7 empty] | 29/01/2025
Pending | EG-1 | EG1-300 | Glycol | 67 | MXK-HV-6718-02 | 8Y ACCESORIS REPL AT SITE MXK-HV-6718-02 | PM | 20642933 | CV-Online | KOMC |  | 27/01/2025 | [7 empty] | 27/01/2025
Pending | EG-1 | EG1-303 | Oxide | 83 | MXK-HV-8300-39 | 8Y ACCESORIS REPL AT SITE MXK-HV-8300-39 | PM | 20642944 | CV-Online | KOMC |  | 21/01/2025 | [7 empty] | 21/01/2025
Pending | EG-1 | EG1-304 | Oxide | 61 | MXK-LV-6130-05 | 8Y ACCESORIS REPL AT SITE MXK-LV-6130-05 | PM | 20642945 | CV-Online | KOMC |  | 23/01/2025 | [7 empty] | 24/01/2025
Pending | ASP | ASP25-025 |  |  | GUK-PSV-706-192 | 3Y PM PSV-706-192 (35T CR) SAMEDAY RETN | PM | 20612606 | PSV-OH | MFT-3 |  | 26/01/2025 | [7 empty] | 28/01/2025 |  |  | 8X6"
Pending | ASP | ASP25-061 |  |  | GUK-HY-0720-08A | 2Y LOPA PROOF TEST OF GUK-FV-720-08A | PM | 20616213 | CV-OH | MFT-3 |  | 20/01/2025 | [7 empty] | 22/01/2025 |  |  | 2"X150#
Pending | ASP | ASP25-062 |  |  | GUK-FV-722-10AR | 2Y LOPA PROOF TEST OF GUK-FV-722-10AR | PM | 20616214 | CV-OH | MFT-3 |  | 20/01/2025 | [7 empty] | 23/01/2025 |  |  | 24"X150#
Pending | ASP | ASP25-070 |  |  | GUK-FV-0706-45 | 2Y O/H OF ACTUATR GUK-FV-0706-45 (SCAFF) | PM | 20624571 | CV-OH | MFT-3 |  | 27/01/2025 | [7 empty] | 29/01/2025 |  |  | 3/4"X300#
Pending | ASP | ASP25-071 |  |  | GUK-FV-0707-45 | 6Y IGV PM GUK-FV-0707-45 DROP WITH ACTUR | PM | 20624572 | CV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 23/01/2025
Pending | ASP | ASP25-126 |  |  | GUK-PV-0726-77 | 8Y VALVE O/H OF GUK-PV-0726-77 | PM | 20535503 | CV-OH | MFT-3 |  | 20/01/2025 | [7 empty] | 21/01/2025 |  |  | 1/2"X300#
Pending | ASP | ASP25-134 |  |  | GUK-LV-0751-02 | 8Y BPCS PM OVERHAUL OF GUK-LV-0751-02 | PM | 20639593 | CV-OH | MFT-3 |  | 21/01/2025 | [7 empty] | 24/01/2025 |  |  | 6"X150#
Pending | ASP | ASP25-145 |  |  | GUK-FV-726-23 | Expander Antisurge is obsolete, need to be replaced. FV-726-23 | BD | 10269675 | CV-Replacement | MFT-3 | O2 Service | 22/01/2025 | [7 empty] | 22/01/2025 |  |  | 6"X300#
Pending | ASP | ASP25-AJ14 |  |  | GUK-HV-722-12 | HV-722-12 to be dropped and overhauled. Report #UT-2024Jun25-139984 | BD | 10280644 | CV-OH | MFT-3 |  | 22/01/2025 | [7 empty] | 25/01/2025 |  |  | 3"X150#
Pending | ASP | ASP25-086 |  |  | GUK-PV-0743-12B | 6Y VLV O/H OF GUK-PV-0743-12B ASP S/D | BD | 10274588 | CV-Replacement |  |  | 25/01/2025 | [7 empty] | 25/01/2025
Pending | ASP | ASP25-146 |  |  | GUK-PDCV 726-71 | PDCV 726-71 to be replaced as per ROTOFLOW (Vendor) recommendation | BD | 10269683 | CV-Replacement |  | O2 Service | 23/01/2025 | [7 empty] | 24/01/2025
Pending | ASP | ASP25-148 |  |  | GUK-V-707 | V-707 Seal gas PCV to be replaced. | BD | 10275533 | CV-Replacement |  |  | 24/01/2025 | [7 empty] | 24/01/2025
Pending | ASP | ASP25-154 |  |  | GUK-HV-714-05R | HV-714-05R to be replaced as it is passing(overhauled in TA 2023,but still passing) | BD | 10269565 | CV-Replacement |  |  | 22/01/2025 | [7 empty] | 23/01/2025
Pending | ASP | ASP25-173 |  |  | GUK-PCV-726-77 | Thrust balancing PCV-726-77 valve to be replaced. | BD | 10269685 | CV-Replacement |  | O2 Service | 24/01/2025 | [7 empty] | 24/01/2025
Pending | ASP | ASP25-155 |  |  | GUK-VKE3-706 | CWS and CWR to be replaced as they are passing | BD | 10270917 | MV-Replacement |  |  | 23/01/2025 | [7 empty] | 24/01/2025
Pending | ASP | ASP25-166 |  |  | GUK-G-728 | G-728 derime inlet valves to be replaced, both to be replaced | BD | 10269679 | MV-Replacement |  | O2 Service | 22/01/2025 | [7 empty] | 22/01/2025
Pending | ASP | ASP25-182 |  |  | GUK-PSV-741-122 | 3/4" Drain Valve (M741-26) to be removed and replaced | BD | 10267451 | MV-Replacement |  | O2 Service | 21/01/2025 | [7 empty] | 21/01/2025
Pending | ASP | ASP25-183 |  |  | GUK-PSV-727-117 | Downstream isolation valve M727-07 is passing, need to be replaced. | BD | 10268591 | MV-Replacement |  | O2 Service | 21/01/2025 | [7 empty] | 21/01/2025
Pending | ASP | ASP25-184 |  |  | GUK-PSV-714-100 | Replacement of inlet 4” manual valve of PSV. | BD | 10269663 | MV-Replacement |  | O2 Service | 20/01/2025 | [7 empty] | 21/01/2025
Pending | ASP | ASP25-185 |  |  | GUK-PSV-714-101 | Replacement of inlet 4” manual valve of PSV. | BD | 10269664 | MV-Replacement |  | O2 Service | 21/01/2025 | [7 empty] | 21/01/2025
Pending | ASP | ASP25-186 |  |  | GUK-PSV-715-100 | Replacement of inlet 4” manual valve of PSV. | BD | 10269665 | MV-Replacement |  | O2 Service | 21/01/2025 | [7 empty] | 22/01/2025
Pending | ASP | ASP25-187 |  |  | GUK-PSV-715-101 | Replacement of inlet 4” manual valve of PSV. | BD | 10269666 | MV-Replacement |  | O2 Service | 22/01/2025 | [7 empty] | 22/01/2025
Pending | ASP | ASP25-193 |  |  | GUK-VKE2-706 | CWS and CWR to be replaced as they are passing | BD | 10270914 | MV-Replacement |  |  | 24/01/2025 | [7 empty] | 24/01/2025
Pending | ASP | ASP25-194 |  |  | GUK-VKE3-707 | CWS and CWR to be replaced as they are passing | BD | 10270916 | MV-Replacement |  |  | 23/01/2025 | [7 empty] | 24/01/2025
Pending | ASP | ASP25-195 |  |  | GUK-VKE2-707 | CWS and CWR to be replaced as they are passing | BD | 10270915 | MV-Replacement |  |  | 22/01/2025 | [7 empty] | 23/01/2025
Pending | ASP | ASP25-AJ15 |  |  | GUK-HY-0722-12 | The NRV at the downstream of HV-722-12 to be checked and repaired. It is suspected that this NRV is passing. | BD | 10280527 | MV-Replacement |  |  | 24/01/2025 | [7 empty] | 25/01/2025
Pending | ASP | ASP25-AJ-22 |  |  | GUK-M708-03 | To replace TRP-708A bypass valve (M708-03) as it is passing. | PM | 10285780 | MV-Replacement |  |  | 25/01/2025 | [7 empty] | 25/01/2025
Pending | DMO | DMO1 | Hydro | 88 | MXK-DEMO-5614 | DEMO JOB DESCRIPTION | DEMO | 54919462 | DEMO | DEMO Workshop | DEMO Additional Details | 30/3/2025 | [7 empty] | 28/3/2025 |  |  | 4 X 4 IN | Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO2 | Hydro | 64 | MXK-DEMO-6567 | DEMO JOB DESCRIPTION | DEMO | 47971218 | DEMO | DEMO Workshop | DEMO Additional Details | 26/2/2025 | [7 empty] | 27/3/2025 |  |  | 9 X 3 IN | Butterfly |  |  |  |  | This is a Demo Item
Pending | DMO | DMO3 | Oxide | 83 | MXK-DEMO-9230 | DEMO JOB DESCRIPTION | DEMO | 85477944 | DEMO | DEMO Workshop | DEMO Additional Details | 27/2/2025 | [7 empty] | 22/3/2025 |  |  | 8 X 3 IN | Globe |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO4 | Oxide | 83 | MXK-DEMO-5649 | DEMO JOB DESCRIPTION | DEMO | 75982913 | DEMO | DEMO Workshop | DEMO Additional Details | 24/1/2025 | [7 empty] | 28/2/2025 |  |  | 8 X 2 IN | 3 Way |  |  |  |  | This is a Demo Item
Pending | DMO | DMO5 | Oxide | 68 | MXK-DEMO-3737 | DEMO JOB DESCRIPTION | DEMO | 34740689 | DEMO | DEMO Workshop | DEMO Additional Details | 29/2/2025 | [7 empty] | 27/1/2025 |  |  | 9 X 10 IN | Angle |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO6 | Glycol | 67 | MXK-DEMO-4066 | DEMO JOB DESCRIPTION | DEMO | 79795523 | DEMO | DEMO Workshop | DEMO Additional Details | 31/3/2025 | [7 empty] | 23/3/2025 |  |  | 4 X 9 IN | Rotary Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO7 | Hydro | 69 | MXK-DEMO-8906 | DEMO JOB DESCRIPTION | DEMO | 25558287 | DEMO | DEMO Workshop | DEMO Additional Details | 22/1/2025 | [7 empty] | 26/1/2025 |  |  | 10 X 2 IN | Angle |  |  |  |  | This is a Demo Item
Pending | DMO | DMO8 | Hydro | 73 | MXK-DEMO-8810 | DEMO JOB DESCRIPTION | DEMO | 49463935 | DEMO | DEMO Workshop | DEMO Additional Details | 24/1/2025 | [7 empty] | 30/2/2025 |  |  | 10 X 6 IN | Angle |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO9 | Hydro | 62 | MXK-DEMO-3821 | DEMO JOB DESCRIPTION | DEMO | 71700904 | DEMO | DEMO Workshop | DEMO Additional Details | 29/2/2025 | [7 empty] | 27/2/2025 |  |  | 5 X 10 IN | Rotary Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO10 | Oxide | 74 | MXK-DEMO-9963 | DEMO JOB DESCRIPTION | DEMO | 52741337 | DEMO | DEMO Workshop | DEMO Additional Details | 28/1/2025 | [7 empty] | 28/1/2025 |  |  | 2 X 4 IN | Angle |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO11 | Oxide | 74 | MXK-DEMO-2402 | DEMO JOB DESCRIPTION | DEMO | 77091794 | DEMO | DEMO Workshop | DEMO Additional Details | 28/1/2025 | [7 empty] | 28/3/2025 |  |  | 8 X 9 IN | Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO12 | Hydro | 60 | MXK-DEMO-5362 | DEMO JOB DESCRIPTION | DEMO | 66405044 | DEMO | DEMO Workshop | DEMO Additional Details | 25/3/2025 | [7 empty] | 30/3/2025 |  |  | 5 X 3 IN | Globe |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO13 | Oxide | 76 | MXK-DEMO-1292 | DEMO JOB DESCRIPTION | DEMO | 67118123 | DEMO | DEMO Workshop | DEMO Additional Details | 20/2/2025 | [7 empty] | 25/1/2025 |  |  | 4 X 5 IN | Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO14 | Hydro | 89 | MXK-DEMO-5360 | DEMO JOB DESCRIPTION | DEMO | 78193969 | DEMO | DEMO Workshop | DEMO Additional Details | 23/2/2025 | [7 empty] | 28/3/2025 |  |  | 4 X 10 IN | Ball |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO15 | Hydro | 61 | MXK-DEMO-8502 | DEMO JOB DESCRIPTION | DEMO | 11905446 | DEMO | DEMO Workshop | DEMO Additional Details | 21/2/2025 | [7 empty] | 29/2/2025 |  |  | 10 X 7 IN | Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO16 | Hydro | 65 | MXK-DEMO-3282 | DEMO JOB DESCRIPTION | DEMO | 77705568 | DEMO | DEMO Workshop | DEMO Additional Details | 23/1/2025 | [7 empty] | 25/1/2025 |  |  | 8 X 8 IN | Ball |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO17 | Hydro | 73 | MXK-DEMO-6346 | DEMO JOB DESCRIPTION | DEMO | 48683133 | DEMO | DEMO Workshop | DEMO Additional Details | 24/2/2025 | [7 empty] | 24/3/2025 |  |  | 1 X 1 IN | Angle |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO18 | Oxide | 65 | MXK-DEMO-1140 | DEMO JOB DESCRIPTION | DEMO | 90523064 | DEMO | DEMO Workshop | DEMO Additional Details | 29/1/2025 | [7 empty] | 21/2/2025 |  |  | 10 X 7 IN | Globe |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO19 | Hydro | 88 | MXK-DEMO-6799 | DEMO JOB DESCRIPTION | DEMO | 80380949 | DEMO | DEMO Workshop | DEMO Additional Details | 21/1/2025 | [7 empty] | 30/2/2025 |  |  | 8 X 6 IN | Rotary Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO20 | Glycol | 89 | MXK-DEMO-5091 | DEMO JOB DESCRIPTION | DEMO | 25982179 | DEMO | DEMO Workshop | DEMO Additional Details | 23/2/2025 | [7 empty] | 21/1/2025 |  |  | 3 X 8 IN | Angle |  |  |  |  | This is a Demo Item
Pending | DMO | DMO21 | Glycol | 60 | MXK-DEMO-1337 | DEMO JOB DESCRIPTION | DEMO | 79297524 | DEMO | DEMO Workshop | DEMO Additional Details | 24/3/2025 | [7 empty] | 22/1/2025 |  |  | 3 X 7 IN | 3 Way |  |  |  |  | This is a Demo Item
Pending | DMO | DMO22 | Oxide | 89 | MXK-DEMO-7870 | DEMO JOB DESCRIPTION | DEMO | 21507512 | DEMO | DEMO Workshop | DEMO Additional Details | 21/2/2025 | [7 empty] | 24/2/2025 |  |  | 2 X 1 IN | Butterfly |  |  |  |  | This is a Demo Item
Pending | DMO | DMO23 | Glycol | 88 | MXK-DEMO-9595 | DEMO JOB DESCRIPTION | DEMO | 66995827 | DEMO | DEMO Workshop | DEMO Additional Details | 23/1/2025 | [7 empty] | 24/3/2025 |  |  | 2 X 1 IN | Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO24 | Oxide | 74 | MXK-DEMO-2591 | DEMO JOB DESCRIPTION | DEMO | 31456055 | DEMO | DEMO Workshop | DEMO Additional Details | 25/3/2025 | [7 empty] | 21/1/2025 |  |  | 7 X 4 IN | Rotary Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO25 | Oxide | 62 | MXK-DEMO-2098 | DEMO JOB DESCRIPTION | DEMO | 84237052 | DEMO | DEMO Workshop | DEMO Additional Details | 24/2/2025 | [7 empty] | 31/3/2025 |  |  | 9 X 2 IN | 3 Way |  |  |  |  | This is a Demo Item
Pending | DMO | DMO26 | Oxide | 68 | MXK-DEMO-5976 | DEMO JOB DESCRIPTION | DEMO | 87439657 | DEMO | DEMO Workshop | DEMO Additional Details | 31/3/2025 | [7 empty] | 24/1/2025 |  |  | 2 X 9 IN | Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO27 | Glycol | 67 | MXK-DEMO-6778 | DEMO JOB DESCRIPTION | DEMO | 42171203 | DEMO | DEMO Workshop | DEMO Additional Details | 29/2/2025 | [7 empty] | 31/3/2025 |  |  | 2 X 2 IN | Rotary Globe |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO28 | Glycol | 74 | MXK-DEMO-2460 | DEMO JOB DESCRIPTION | DEMO | 34209466 | DEMO | DEMO Workshop | DEMO Additional Details | 23/1/2025 | [7 empty] | 23/3/2025 |  |  | 1 X 5 IN | Butterfly |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO29 | Oxide | 83 | MXK-DEMO-4112 | DEMO JOB DESCRIPTION | DEMO | 26390405 | DEMO | DEMO Workshop | DEMO Additional Details | 22/1/2025 | [7 empty] | 20/3/2025 |  |  | 8 X 7 IN | Angle |  |  |  |  | This is a Demo Item
Pending | DMO | DMO30 | Glycol | 70 | MXK-DEMO-6451 | DEMO JOB DESCRIPTION | DEMO | 51208386 | DEMO | DEMO Workshop | DEMO Additional Details | 28/3/2025 | [7 empty] | 20/2/2025 |  |  | 10 X 4 IN | Rotary Globe |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO31 | Hydro | 71 | MXK-DEMO-9837 | DEMO JOB DESCRIPTION | DEMO | 85621432 | DEMO | DEMO Workshop | DEMO Additional Details | 25/2/2025 | [7 empty] | 25/1/2025 |  |  | 1 X 3 IN | Angle |  |  |  |  | This is a Demo Item
Pending | DMO | DMO32 | Oxide | 82 | MXK-DEMO-6294 | DEMO JOB DESCRIPTION | DEMO | 35639722 | DEMO | DEMO Workshop | DEMO Additional Details | 24/3/2025 | [7 empty] | 31/1/2025 |  |  | 7 X 8 IN | Angle |  |  |  |  | This is a Demo Item
Pending | DMO | DMO33 | Glycol | 68 | MXK-DEMO-5453 | DEMO JOB DESCRIPTION | DEMO | 67931597 | DEMO | DEMO Workshop | DEMO Additional Details | 24/2/2025 | [7 empty] | 25/3/2025 |  |  | 3 X 10 IN | Ball |  |  |  |  | This is a Demo Item
Pending | DMO | DMO34 | Hydro | 68 | MXK-DEMO-5135 | DEMO JOB DESCRIPTION | DEMO | 69255064 | DEMO | DEMO Workshop | DEMO Additional Details | 24/1/2025 | [7 empty] | 28/2/2025 |  |  | 10 X 9 IN | Butterfly |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO35 | Hydro | 79 | MXK-DEMO-9718 | DEMO JOB DESCRIPTION | DEMO | 34587032 | DEMO | DEMO Workshop | DEMO Additional Details | 21/2/2025 | [7 empty] | 24/3/2025 |  |  | 3 X 5 IN | Ball |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO36 | Glycol | 90 | MXK-DEMO-4923 | DEMO JOB DESCRIPTION | DEMO | 49521290 | DEMO | DEMO Workshop | DEMO Additional Details | 27/3/2025 | [7 empty] | 22/3/2025 |  |  | 8 X 9 IN | Butterfly |  |  |  |  | This is a Demo Item
Pending | DMO | DMO37 | Glycol | 61 | MXK-DEMO-6677 | DEMO JOB DESCRIPTION | DEMO | 70252135 | DEMO | DEMO Workshop | DEMO Additional Details | 31/2/2025 | [7 empty] | 30/3/2025 |  |  | 7 X 7 IN | Ball |  |  |  |  | This is a Demo Item
Pending | DMO | DMO38 | Hydro | 76 | MXK-DEMO-8042 | DEMO JOB DESCRIPTION | DEMO | 90428659 | DEMO | DEMO Workshop | DEMO Additional Details | 26/1/2025 | [7 empty] | 25/3/2025 |  |  | 8 X 9 IN | Globe |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO39 | Glycol | 85 | MXK-DEMO-6490 | DEMO JOB DESCRIPTION | DEMO | 41570770 | DEMO | DEMO Workshop | DEMO Additional Details | 24/3/2025 | [7 empty] | 21/1/2025 |  |  | 4 X 4 IN | 3 Way |  |  |  |  | This is a Demo Item
Pending | DMO | DMO40 | Oxide | 79 | MXK-DEMO-6922 | DEMO JOB DESCRIPTION | DEMO | 92403010 | DEMO | DEMO Workshop | DEMO Additional Details | 20/1/2025 | [7 empty] | 29/2/2025 |  |  | 7 X 4 IN | Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO41 | Glycol | 89 | MXK-DEMO-4367 | DEMO JOB DESCRIPTION | DEMO | 61186344 | DEMO | DEMO Workshop | DEMO Additional Details | 30/1/2025 | [7 empty] | 28/1/2025 |  |  | 8 X 8 IN | Globe |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO42 | Glycol | 65 | MXK-DEMO-4098 | DEMO JOB DESCRIPTION | DEMO | 91232076 | DEMO | DEMO Workshop | DEMO Additional Details | 25/1/2025 | [7 empty] | 29/3/2025 |  |  | 1 X 9 IN | 3 Way |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO43 | Oxide | 67 | MXK-DEMO-2217 | DEMO JOB DESCRIPTION | DEMO | 38754585 | DEMO | DEMO Workshop | DEMO Additional Details | 21/3/2025 | [7 empty] | 21/3/2025 |  |  | 7 X 8 IN | 3 Way |  |  |  |  | This is a Demo Item
Pending | DMO | DMO44 | Oxide | 66 | MXK-DEMO-2881 | DEMO JOB DESCRIPTION | DEMO | 99913422 | DEMO | DEMO Workshop | DEMO Additional Details | 26/1/2025 | [7 empty] | 31/1/2025 |  |  | 10 X 1 IN | Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO45 | Glycol | 61 | MXK-DEMO-8008 | DEMO JOB DESCRIPTION | DEMO | 87144514 | DEMO | DEMO Workshop | DEMO Additional Details | 25/2/2025 | [7 empty] | 31/2/2025 |  |  | 6 X 8 IN | Angle |  |  |  |  | This is a Demo Item
Pending | DMO | DMO46 | Oxide | 69 | MXK-DEMO-1066 | DEMO JOB DESCRIPTION | DEMO | 83713142 | DEMO | DEMO Workshop | DEMO Additional Details | 25/2/2025 | [7 empty] | 20/1/2025 |  |  | 9 X 1 IN | 3 Way |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO47 | Glycol | 64 | MXK-DEMO-2371 | DEMO JOB DESCRIPTION | DEMO | 28726448 | DEMO | DEMO Workshop | DEMO Additional Details | 24/2/2025 | [7 empty] | 25/1/2025 |  |  | 10 X 8 IN | Rotary Globe |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO48 | Oxide | 70 | MXK-DEMO-3344 | DEMO JOB DESCRIPTION | DEMO | 96595437 | DEMO | DEMO Workshop | DEMO Additional Details | 28/3/2025 | [7 empty] | 25/2/2025 |  |  | 2 X 8 IN | Globe |  |  |  |  | This is a Demo Item
Pending | DMO | DMO49 | Oxide | 66 | MXK-DEMO-6628 | DEMO JOB DESCRIPTION | DEMO | 16395016 | DEMO | DEMO Workshop | DEMO Additional Details | 21/1/2025 | [7 empty] | 26/2/2025 |  |  | 7 X 10 IN | Rotary Globe |  |  | Yes |  | This is a Demo Item
Pending | DMO | DMO50 | Glycol | 66 | MXK-DEMO-2296 | DEMO JOB DESCRIPTION | DEMO | 50386900 | DEMO | DEMO Workshop | DEMO Additional Details | 26/2/2025 | [7 empty] | 26/2/2025 |  |  | 4 X 5 IN | Rotary Globe |  |  |  |  | This is a Demo Item